## Sheet1
DECISION TREE ANALYSIS [5 Tier Scenario]
| Project ID |  | FOR ESTIMATING A SCHEDULE BUFFER & MANAGEMENT RESERVE BUDGET | [14 empty] | © 2012. Dr. Kenneth F. Smith, PMP
[6 empty] | An "A Priori Analysis" of Possible Outcomes for [Up to Five] Mutually Independent Risks | [9 empty] | "Murphy Cascade" i.e. YOUR Estimated IMPACT if ALL KNOWN RISKS Occur
[7 empty] | Enter Risks and data in the Yellow Cells Below | [9 empty] | Murphy Cascade = All Risks Occur
|  | OBJECTIVE | RISK 1 |  | RISK 2 |  | RISK 3 |  | RISK 4 |  | RISK 5 | [5 empty] | 8.219e-15% | = Cascade Rate |  | Computation Basis
|  | PLANNED SCHEDULE | Probability | Impact | Probability | Impact | Probability | Impact | Probability | Impact | Probability | Impact | Probability* | EXPECTED IMPACT | TOTAL "As is" IMPACT |  | Added Cumulative Cascade Effect | SUGGESTED CONTINGENCY SCHEDULE & BUDGET | SUGGESTED REVISED SCHEDULE & BUDGET | Actual Number of Risks in Each Scenario | Effect in Each Scenario
|  |  | Poor Design | Ceiling Estimate | Unavailable Skills | Ceiling Estimate | Equipment Breakdown | Ceiling Estimate | Bad Weather | Ceiling Estimate | Civil Disorder | Ceiling Estimate | of Occurrence | for CONTINGENCY | SCENARIO OVERUN
| Time Unit = | days |  | days |  | days |  | days |  | days |  | days |  |  | days | days | days | days | days
Alt | Input Drivers: | 100 | 37% | 1 | 35% | 1 | 20% | 1 | 30% | 1 | 20% | 1 | 100% | 1.42% | 5 | 5 | 1.42 | 6.42 | 106.42
| Money Unit | $m |  | $m |  | $m |  | $m |  | $m |  | $m |  |  | $m | $m | $m | $m | $m
| Input Drivers: | 200 | 37% | 1 | 35% | 1 | 20% | 1 | 30% | 1 | 20% | 1 | 98.86% | 1.373% | 5 | 5 | 1.42 | 6.42 | 206.42
1 | WORST CASE = "Murphy" |  | 37% | 1 | 35% | 1 | 20% | 1 | 30% | 1 | 20% | 1 | 0.1554% | 0.00777 | 5 |  | 0.00777 |  |  | 5 | 5
2 |  |  | 37% | 1 | 35% | 1 | 20% | 1 | 30% | 1 | 80% | 0 | 0.6216% | 0.024864 | 4 |  | 0.024864 |  |  | 4 | 4
3 |  |  | 37% | 1 | 35% | 1 | 20% | 1 | 70% | 0 | 20% | 1 | 0.3626% | 0.014504 | 4 |  | 0.014504 |  |  | 4 | 4
4 |  |  | 37% | 1 | 35% | 1 | 20% | 1 | 70% | 0 | 80% | 0 | 1.45% | 0.043512 | 3 |  | 0.043512 |  |  | 3 | 3
5 |  |  | 37% | 1 | 35% | 1 | 80% | 0 | 30% | 1 | 20% | 1 | 0.6216% | 0.024864 | 4 |  | 0.024864 |  |  | 4 | 4
6 |  |  | 37% | 1 | 35% | 1 | 80% | 0 | 30% | 1 | 80% | 0 | 2.486% | 0.074592 | 3 |  | 0.074592 |  |  | 3 | 3
7 |  |  | 37% | 1 | 35% | 1 | 80% | 0 | 70% | 0 | 20% | 1 | 1.45% | 0.043512 | 3 |  | 0.043512 |  |  | 3 | 3
8 |  |  | 37% | 1 | 35% | 1 | 80% | 0 | 70% | 0 | 80% | 0 | 5.802% | 0.11603 | 2 |  | 0.11603 |  |  | 2 | 2
9 |  |  | 37% | 1 | 65% | 0 | 20% | 1 | 30% | 1 | 20% | 1 | 0.2886% | 0.011544 | 4 |  | 0.011544 |  |  | 4 | 4
10 |  |  | 37% | 1 | 65% | 0 | 20% | 1 | 30% | 1 | 80% | 0 | 1.154% | 0.034632 | 3 |  | 0.034632 |  |  | 3 | 3
11 |  |  | 37% | 1 | 65% | 0 | 20% | 1 | 70% | 0 | 20% | 1 | 0.6734% | 0.020202 | 3 |  | 0.020202 |  |  | 3 | 3
12 |  |  | 37% | 1 | 65% | 0 | 20% | 1 | 70% | 0 | 80% | 0 | 2.694% | 0.053872 | 2 |  | 0.053872 |  |  | 2 | 2
13 |  |  | 37% | 1 | 65% | 0 | 80% | 0 | 30% | 1 | 20% | 1 | 1.154% | 0.034632 | 3 |  | 0.034632 |  |  | 3 | 3
14 |  |  | 37% | 1 | 65% | 0 | 80% | 0 | 30% | 1 | 80% | 0 | 4.618% | 0.092352 | 2 |  | 0.092352 |  |  | 2 | 2
15 |  |  | 37% | 1 | 65% | 0 | 80% | 0 | 70% | 0 | 20% | 1 | 2.694% | 0.053872 | 2 |  | 0.053872 |  |  | 2 | 2
16 |  |  | 37% | 1 | 65% | 0 | 80% | 0 | 70% | 0 | 80% | 0 | 10.77% | 0.10774 | 1 |  | 0.10774 |  |  | 1 | 1
17 |  |  | 63% | 0 | 35% | 1 | 20% | 1 | 30% | 1 | 20% | 1 | 0.2646% | 0.010584 | 4 |  | 0.010584 |  |  | 4 | 4
18 |  |  | 63% | 0 | 35% | 1 | 20% | 1 | 30% | 1 | 80% | 0 | 1.058% | 0.031752 | 3 |  | 0.031752 |  |  | 3 | 3
19 |  |  | 63% | 0 | 35% | 1 | 20% | 1 | 70% | 0 | 20% | 1 | 0.6174% | 0.018522 | 3 |  | 0.018522 |  |  | 3 | 3
20 |  |  | 63% | 0 | 35% | 1 | 20% | 1 | 70% | 0 | 80% | 0 | 2.47% | 0.049392 | 2 |  | 0.049392 |  |  | 2 | 2
21 |  |  | 63% | 0 | 35% | 1 | 80% | 0 | 30% | 1 | 20% | 1 | 1.058% | 0.031752 | 3 |  | 0.031752 |  |  | 2 | 3
22 |  |  | 63% | 0 | 35% | 1 | 80% | 0 | 30% | 1 | 80% | 0 | 4.234% | 0.084672 | 2 |  | 0.084672 |  |  | 2 | 2
23 |  |  | 63% | 0 | 35% | 1 | 80% | 0 | 70% | 0 | 20% | 1 | 2.47% | 0.049392 | 2 |  | 0.049392 |  |  | 2 | 2
24 |  |  | 63% | 0 | 35% | 1 | 80% | 0 | 70% | 0 | 80% | 0 | 9.878% | 0.098784 | 1 |  | 0.098784 |  |  | 1 | 1
25 |  |  | 63% | 0 | 65% | 0 | 20% | 1 | 30% | 1 | 20% | 1 | 0.4914% | 0.014742 | 3 |  | 0.014742 |  |  | 3 | 3
26 |  |  | 63% | 0 | 65% | 0 | 20% | 1 | 30% | 1 | 80% | 0 | 1.966% | 0.039312 | 2 |  | 0.039312 |  |  | 2 | 2
27 |  |  | 63% | 0 | 65% | 0 | 20% | 1 | 70% | 0 | 20% | 1 | 1.147% | 0.022932 | 2 |  | 0.022932 |  |  | 2 | 2
28 |  |  | 63% | 0 | 65% | 0 | 20% | 1 | 70% | 0 | 80% | 0 | 4.586% | 0.045864 | 1 |  | 0.045864 |  |  | 1 | 1
29 |  |  | 63% | 0 | 65% | 0 | 80% | 0 | 30% | 1 | 20% | 1 | 1.966% | 0.039312 | 2 |  | 0.039312 |  |  | 2 | 2
30 |  |  | 63% | 0 | 65% | 0 | 80% | 0 | 30% | 1 | 80% | 0 | 7.862% | 0.078624 | 1 |  | 0.078624 |  |  | 1 | 1
31 |  |  | 63% | 0 | 65% | 0 | 80% | 0 | 70% | 0 | 20% | 1 | 4.586% | 0.045864 | 1 |  | 0.045864 |  |  | 1 | 1
32 | BEST CASE = "Pollyanna" |  | 63% | 0 | 65% | 0 | 80% | 0 | 70% | 0 | 80% | 0 | 18.35% | 0 | 0 |  | 0 |  |  | 0 | 0
|  | An "A Priori Analysis" of Possible Outcomes for [Up to Five] Mutually Independent Risks | [13 empty] | "Murphy Cascade" i.e. YOUR Estimated IMPACT if ALL KNOWN RISKS Occur
[17 empty] | Murphy Cascade = All Risks Occur |  |  | Computation Basis
|  | OBJECTIVE | RISK 1 |  | RISK 2 |  | RISK 3 |  | RISK 4 |  | RISK 5 | [5 empty] | 8.219e-15% | = Cascade Rate
|  | PLANNED BUDGET | Probability | Impact | Probability | Impact | Probability | Impact | Probability | Impact | Probability | Impact | Probability* | EXPECTED IMPACT | TOTAL "As is" IMPACT |  | Added Cumulative Cascade Effect | SUGGESTED CONTINGENCY BUDGET |  | Actual Number of Risks in Each Scenario | Effect in Each Scenario
|  |  | Design Flaw | Ceiling Estimate | Expertise Not Available | Ceiling Estimate | Equipment Breakdown | Ceiling Estimate | Bad Weather | Ceiling Estimate | Civil Disorder | Ceiling Estimate | of Occurrence | for CONTINGENCY | SCENARIO OVERUN
| Time Unit = | $m |  | $m |  | $m |  | $m |  | $m |  | $m |  |  | $m | $m | $m | $m
Alt | Input Drivers: | 200 | 37% | 1 | 35% | 1 | 20% | 1 | 30% | 1 | 20% | 1 | 100% | 1.42% | 5 | 5 | 1.42 | 6.42
1 | WORST CASE = "Murphy" |  | 37% | 1 | 35% | 1 | 20% | 1 | 30% | 1 | 20% | 1 | 0.1554% | 0.00777 | 5 |  | 0.00777 |  |  | 5 | 5
2 |  |  | 37% | 1 | 35% | 1 | 20% | 1 | 30% | 1 | 80% | 0 | 0.6216% | 0.024864 | 4 |  | 0.024864 |  |  | 4 | 4
3 |  |  | 37% | 1 | 35% | 1 | 20% | 1 | 70% | 0 | 20% | 1 | 0.3626% | 0.014504 | 4 |  | 0.014504 |  |  | 4 | 4
4 |  |  | 37% | 1 | 35% | 1 | 20% | 1 | 70% | 0 | 80% | 0 | 1.45% | 0.043512 | 3 |  | 0.043512 |  |  | 3 | 3
5 |  |  | 37% | 1 | 35% | 1 | 80% | 0 | 30% | 1 | 20% | 1 | 0.6216% | 0.024864 | 4 |  | 0.024864 |  |  | 4 | 4
6 |  |  | 37% | 1 | 35% | 1 | 80% | 0 | 30% | 1 | 80% | 0 | 2.486% | 0.074592 | 3 |  | 0.074592 |  |  | 3 | 3
7 |  |  | 37% | 1 | 35% | 1 | 80% | 0 | 70% | 0 | 20% | 1 | 1.45% | 0.043512 | 3 |  | 0.043512 |  |  | 3 | 3
8 |  |  | 37% | 1 | 35% | 1 | 80% | 0 | 70% | 0 | 80% | 0 | 5.802% | 0.11603 | 2 |  | 0.11603 |  |  | 2 | 2
9 |  |  | 37% | 1 | 65% | 0 | 20% | 1 | 30% | 1 | 20% | 1 | 0.2886% | 0.011544 | 4 |  | 0.011544 |  |  | 4 | 4
10 |  |  | 37% | 1 | 65% | 0 | 20% | 1 | 30% | 1 | 80% | 0 | 1.154% | 0.034632 | 3 |  | 0.034632 |  |  | 3 | 3
11 |  |  | 37% | 1 | 65% | 0 | 20% | 1 | 70% | 0 | 20% | 1 | 0.6734% | 0.020202 | 3 |  | 0.020202 |  |  | 3 | 3
12 |  |  | 37% | 1 | 65% | 0 | 20% | 1 | 70% | 0 | 80% | 0 | 2.694% | 0.053872 | 2 |  | 0.053872 |  |  | 2 | 2
13 |  |  | 37% | 1 | 65% | 0 | 80% | 0 | 30% | 1 | 20% | 1 | 1.154% | 0.034632 | 3 |  | 0.034632 |  |  | 3 | 3
14 |  |  | 37% | 1 | 65% | 0 | 80% | 0 | 30% | 1 | 80% | 0 | 4.618% | 0.092352 | 2 |  | 0.092352 |  |  | 2 | 2
15 |  |  | 37% | 1 | 65% | 0 | 80% | 0 | 70% | 0 | 20% | 1 | 2.694% | 0.053872 | 2 |  | 0.053872 |  |  | 2 | 2
16 |  |  | 37% | 1 | 65% | 0 | 80% | 0 | 70% | 0 | 80% | 0 | 10.77% | 0.10774 | 1 |  | 0.10774 |  |  | 1 | 1
17 |  |  | 63% | 0 | 35% | 1 | 20% | 1 | 30% | 1 | 20% | 1 | 0.2646% | 0.010584 | 4 |  | 0.010584 |  |  | 4 | 4
18 |  |  | 63% | 0 | 35% | 1 | 20% | 1 | 30% | 1 | 80% | 0 | 1.058% | 0.031752 | 3 |  | 0.031752 |  |  | 3 | 3
19 |  |  | 63% | 0 | 35% | 1 | 20% | 1 | 70% | 0 | 20% | 1 | 0.6174% | 0.018522 | 3 |  | 0.018522 |  |  | 3 | 3
20 |  |  | 63% | 0 | 35% | 1 | 20% | 1 | 70% | 0 | 80% | 0 | 2.47% | 0.049392 | 2 |  | 0.049392 |  |  | 2 | 2
21 |  |  | 63% | 0 | 35% | 1 | 80% | 0 | 30% | 1 | 20% | 1 | 1.058% | 0.031752 | 3 |  | 0.031752 |  |  | 2 | 3
22 |  |  | 63% | 0 | 35% | 1 | 80% | 0 | 30% | 1 | 80% | 0 | 4.234% | 0.084672 | 2 |  | 0.084672 |  |  | 2 | 2
23 |  |  | 63% | 0 | 35% | 1 | 80% | 0 | 70% | 0 | 20% | 1 | 2.47% | 0.049392 | 2 |  | 0.049392 |  |  | 2 | 2
24 |  |  | 63% | 0 | 35% | 1 | 80% | 0 | 70% | 0 | 80% | 0 | 9.878% | 0.098784 | 1 |  | 0.098784 |  |  | 1 | 1
25 |  |  | 63% | 0 | 65% | 0 | 20% | 1 | 30% | 1 | 20% | 1 | 0.4914% | 0.014742 | 3 |  | 0.014742 |  |  | 3 | 3
26 |  |  | 63% | 0 | 65% | 0 | 20% | 1 | 30% | 1 | 80% | 0 | 1.966% | 0.039312 | 2 |  | 0.039312 |  |  | 2 | 2
27 |  |  | 63% | 0 | 65% | 0 | 20% | 1 | 70% | 0 | 20% | 1 | 1.147% | 0.022932 | 2 |  | 0.022932 |  |  | 2 | 2
28 |  |  | 63% | 0 | 65% | 0 | 20% | 1 | 70% | 0 | 80% | 0 | 4.586% | 0.045864 | 1 |  | 0.045864 |  |  | 1 | 1
29 |  |  | 63% | 0 | 65% | 0 | 80% | 0 | 30% | 1 | 20% | 1 | 1.966% | 0.039312 | 2 |  | 0.039312 |  |  | 2 | 2
30 |  |  | 63% | 0 | 65% | 0 | 80% | 0 | 30% | 1 | 80% | 0 | 7.862% | 0.078624 | 1 |  | 0.078624 |  |  | 1 | 1
31 |  |  | 63% | 0 | 65% | 0 | 80% | 0 | 70% | 0 | 20% | 1 | 4.586% | 0.045864 | 1 |  | 0.045864 |  |  | 1 | 1
32 | BEST CASE = "Pollyanna" |  | 63% | 0 | 65% | 0 | 80% | 0 | 70% | 0 | 80% | 0 | 18.35% | 0 | 0 |  | 0 |  |  | 0 | 0
© 2012. Dr. Kenneth F. Smith, PMP
This Program was developed by Dr. Ken Smith, PMP
to make your life easier in planning projects & analyzing data
If you would like further technical assistance with
Program/Project Design, Monitoring &/or Evaluation
Either On-the-Job, or in Workshop Training
|  |  | Please | EMail: kenfsmith@aol.com
|  |  | Aiding the World's Projects |  | Have Laptop, will travel